## 1 (hidden)
Status | Count
Completed | 17
In Progress | 157
Not Started | 13
Grand Total | 187

## 2 (hidden)
Department | Budget | Cost
Cardiology | 2136135.01 | 1178413.69
Emergency | 14681343.26 | 5435169.74
ICU | 2326073.4 | 1869049.75
ID | 310073 | 268750.97
IM | 4730212.92 | 2152988.09
OB/GYN | 745080.88 | 580684.07
Oncology | 4539983.36 | 1217393.58
Orthopedics | 1396126.67 | 921794.67
Outpatient | 1218767.09 | 689138.83
Pediatrics | 1249260.32 | 726256.98
Pharmacy | 1829810.08 | 1386035.32
Radiology | 2416970.13 | 1249826.01
Surgery | 8720448.1 | 5439411.26
Grand Total | 46300284.22 | 23114912.96

## 3 (hidden)
Priority | Count of Project ID
Critical | 35
High | 80
Low | 15
Medium | 57
Grand Total | 187

## Project Management Dashboard
EHR Project Management Dashboard
Facility | Department | Project Type | PM Name | Start Date | End Date | Duration Days | Tasks Total | Tasks Completed | Percent Complete
Al Noor Hospital | Cardiology | Equipment Procurement | Youssef Younis | 2023-02-25 | 2023-03-09 | 12 | 12 | 3 | 25%
| Emergency | Equipment Procurement | Omar Hassan | 2023-03-17 | 2023-04-13 | 27 | 24 | 6 | 25%
| Oncology | Equipment Procurement | Mona Aziz | 2023-01-29 | 2023-03-13 | 43 | 36 | 13 | 36.11%
|  |  | Youssef Ismail | 2023-01-10 | 2023-01-29 | 19 | 10 | 0 | 0%
| Radiology | Equipment Procurement | Hany Younis | 2023-01-22 | 2023-03-13 | 50 | 16 | 8 | 50%
|  |  | Omar El Sayed | 2023-02-10 | 2023-03-18 | 36 | 36 | 15 | 41.67%
| Surgery | Equipment Procurement | Hany Ismail | 2023-02-17 | 2023-04-11 | 53 | 13 | 6 | 46.15%
|  |  | Hany Mahmoud | 2023-03-13 | 2023-05-18 | 66 | 10 | 4 | 40%
Central Medical Center | Cardiology | Equipment Procurement | Amira Saleh | 2023-03-04 | 2023-04-09 | 36 | 91 | 50 | 54.95%
| Emergency | Equipment Procurement | Ahmed Saleh | 2023-01-12 | 2023-01-20 | 8 | 10 | 0 | 0%
|  |  | Omar Ibrahim | 2023-03-20 | 2023-03-28 | 8 | 21 | 1 | 4.762%
|  |  | Sarah El Sayed | 2023-03-15 | 2023-03-22 | 7 | 13 | 4 | 30.77%
| ICU | Equipment Procurement | Youssef Ismail | 2023-01-08 | 2023-01-28 | 20 | 13 | 13 | 1
| IM | Equipment Procurement | Sarah Hamdy | 2023-01-17 | 2023-03-30 | 72 | 15 | 7 | 0.46667
| Orthopedics | Equipment Procurement | Laila Saleh | 2023-01-05 | 2023-01-29 | 24 | 18 | 5 | 27.78%
|  |  | Sarah Farouk | 2023-02-01 | 2023-03-08 | 35 | 500 | 141 | 28.2%
| Radiology | Equipment Procurement | Ahmed Younis | 2023-03-14 | 2023-03-30 | 16 | 77 | 14 | 18.18%
|  |  | Laila Ismail | 2023-03-30 | 2023-05-01 | 32 | 18 | 1 | 5.556%
Eastside Cardio Institute | IM | Equipment Procurement | Karim Farouk | 2023-03-27 | 2023-06-15 | 80 | 25 | 20 | 0.8
| Pharmacy | Equipment Procurement | Dina Hassan | 2023-02-02 | 2023-03-31 | 57 | 500 | 310 | 62%
Green Valley Clinic | Emergency | Equipment Procurement | Sarah Ibrahim | 2023-03-16 | 2023-03-25 | 9 | 20 | 9 | 45%
| IM | Equipment Procurement | Mona Ibrahim | 2023-01-22 | 2023-02-07 | 16 | 33 | 33 | 1
| OB/GYN | Equipment Procurement | Farah El Sayed | 2023-03-09 | 2023-04-08 | 30 | 125 | 47 | 37.6%
Riverbend Hospital | IM | Equipment Procurement | Laila Ismail | 2023-02-18 | 2023-02-28 | 10 | 417 | 85 | 0.20384
| Outpatient | Equipment Procurement | Tarek Mahmoud | 2023-01-19 | 2023-03-04 | 44 | 12 | 2 | 16.67%
| Pediatrics | Equipment Procurement | Hassan Saleh | 2023-02-18 | 2023-03-17 | 27 | 10 | 2 | 20%
| Pharmacy | Equipment Procurement | Hany Ismail | 2023-01-19 | 2023-02-25 | 37 | 21 | 7 | 33.33%
| Surgery | Equipment Procurement | Amira Mostafa | 2023-03-19 | 2023-11-24 | 250 | 111 | 56 | 50.45%
St. Mary’s Health | Emergency | Equipment Procurement | Laila Saleh | 2023-02-09 | 2023-03-27 | 46 | 16 | 13 | 81.25%
| IM | Equipment Procurement | Hany Mostafa | 2023-02-20 | 2023-03-14 | 22 | 70 | 20 | 0.28571
|  |  | Youssef Younis | 2023-03-27 | 2023-07-22 | 117 | 13 | 5 | 0.38462
Sunrise Children’s | Emergency | Equipment Procurement | Omar Mahmoud | 2023-03-03 | 2023-04-15 | 43 | 17 | 17 | 1
| ICU | Equipment Procurement | Hany Ibrahim | 2023-01-28 | 2023-03-01 | 32 | 21 | 4 | 19.05%
| Pharmacy | Equipment Procurement | Sarah El Sayed | 2023-01-24 | 2023-02-03 | 10 | 23 | 16 | 69.57%
Grand Total
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## 11 (hidden)
Sum of Projects Budgets | 6041680.56
Number of Projects | 187
Number of Projects by project type | 8
AvgBudgetPerProject | 32308.4522
AvgBudgetPerProject by Project Type | 755210.07
Average of Readmission Rate Change | -49.2%
Average of Mortality Rate Change | -2.109%
Average of Satisfaction Change | 2.8109
Average of Change Requests | 1.3529
Average of Scope Creep Score | 22.1348
Average of Documentation Completeness | 24.0112
Average of Effort Hours | 768.4171
Average of Team Size | 8.6845

## 12 (hidden)
Month | Average of Readmission Rate Change Pct | Average of Mortality Rate Change Pct
January | -48.39% | -2.22%
February | -68.77% | 0.7946%
March | -31.88% | -4.688%
Grand Total | -49.2% | -0.021091

## 25 (hidden)
Documentation Completeness | Scope Creepe Scope
13.1 | 10.8
16.4 | 22.9
3.9 | 7.7
53.5 | 93.4
18.3 | 19.8
4.4 | 34.6
1.9 | 13.3
68.5 | 6.6
13.3 | 4.8
31 | 4
29.5 | 8.5
70.8 | 21.4
15.1 | 9.6
8.3 | 50.2
27.6 | 4.8
28.8 | 14.8
28.4 | 25
44.2 | 6.7
54.6 | 22.9
25.1 | 56
0.6 | 17.1
5.9 | 20
18.2 | 48.5
30.7 | 15.4
24.3 | 5.3
22.1 | 3.5
5.5 | 34.4
2.8 | 38.2
12.5 | 8.9
44.4 | 71.7
12.6 | 2.7
26.4 | 17.4
7.1 | 13
0.2 | 11.6
19.6 | 34.7
38.2 | 10.4
22.2 | 2.3
16.5 | 4.7
1.2 | 12.9
72.2 | 21.4
64 | 34.5
60.4 | 51.3
2.1 | 9.5
11.1 | 16.5
11.7 | 11.7
38.4 | 8.2
5.7 | 6.5
35.6 | 7.2
18.6 | 24.9
15.1 | 15.6
12.4 | 23.3
18.2 | 4.3
10.7 | 28.2
15.6 | 15
6 | 46.3
2.9 | 14.1
9 | 13.8
4.9 | 26.6
19.5 | 11.6
42.2 | 4.6
10.9 | 14.9
17.8 | 13.2
54.9 | 41
0.3 | 27.6
9.9 | 46.7
52.5 | 15.2
30.3 | 3.7
10.5 | 89
20.7 | 12.6
14.3 | 36.5
24.6 | 8.4
27 | 4.2
11.9 | 10.1
48.1 | 11.1
27.9 | 23.4
79.1 | 47.1
43.9 | 1.6
21.3 | 13.8
15.3 | 22
3.2 | 4.7
14.3 | 40.6
15.2 | 55.3
3 | 2.9
8.5 | 12.8
12.3 | 20.5
31.8 | 9.6
6.3 | 93.7
60.4 | 71.6
1.6 | 31.9
28.4 | 27.7
37 | 19.6
62.8 | 4.3
12 | 22.2
35.6 | 3.3
51.2 | 30.4
6.9 | 7.3
27.1 | 13.2
6.5 | 38
8.1 | 9.4
20.1 | 7.6
5.9 | 21.8
18.3 | 4.3
69.7 | 51.8
19.2 | 15.5
12.1 | 41.2
32.8 | 54.2
13.7 | 12.7
23.4 | 19.9
23.3 | 21.1
32.2 | 31.3
5.5 | 40.6
4.9 | 15.2
69.4 | 3.8
52.1 | 15.1
3.4 | 10.9
9.7 | 7
23 | 14.1
57.2 | 12.5
54.5 | 26.7
3.5 | 13
14 | 10
13.9 | 98.6
6.4 | 23.9
4.9 | 22.8
8.5 | 8
23.4 | 8.9
17.9 | 2.6
22.7 | 40.4
40 | 100
4.7 | 30.3
20.9 | 18.1
27 | 25.3
20.1 | 4.1
28.8 | 15.7
56.1 | 10.7
18 | 37.8
56.4 | 19.9
3.2 | 18.7
37.4 | 10.8
5.2 | 20.8
53.3 | 12.1
12.6 | 13.4
33.1 | 25.9
16.8 | 4.6
80.1 | 38
38.3 | 8.5
12.6 | 7.7
27.1 | 47.5
20.7 | 33.8
9.3 | 7.5
0.7 | 7.7
9.9 | 37.8
53.7 | 10.5
9.8 | 27.7
23.2 | 5.8
33.3 | 22.1
8.7 | 24.4
42.8 | 5.2
64.7 | 54.2
28.8 | 5.6
9.2 | 15.3
22.8 | 21
34.1 | 31.3
37.7 | 29.8
6.1 | 6.2
20.3 | 32.9
10.4 | 46.6
28.6 | 7.1
13.9 | 11.9
27.1 | 23.3
26.7 | 80.5
85.9 | 43
13.9 | 7.4
8.6 | 30.3
4.4 | 5
19.3 | 7.2
17.8 | 12
27.3 | 27.1
53.7 | 8.9
34.3 | 6.7
11.6 | 8.4
0.4 | 27.4
11.2 | 31.3
33.7 | 32.6
7.7 | 18.4
38.8 | 25.2
24.3 | 8
0
0

## 15 (hidden)
Total Budget | 46300284.22
Total Cost | 23114912.96
Not Started | 13
In Progress | 157
Completed | 17

## 18 (hidden)
Region | Count
Alexandria | 34
Greater Cairo | 88
Nile Delta | 28
Red Sea | 5
Sinai | 4
Upper Egypt | 28
Grand Total | 187

## Dashboard
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
EHR Project Performance View
8660 Total Tasks
3370 Completed Tasks
1.35 Change Requests

## KPIs (hidden)
Average of Effort hours | 768.4171
Completion Rate | 40.86%
Average of Change Request | 1.3529
Total Tasks | 8660
Tasks Completed | 3370
Total Effort Hours | 143694

## 19 (hidden)
Average of Satisfaction Change | Average of Effort Hours | Average of Change Requests | Average of Team Size
2.8109 | 768.4171 | 1.3529 | 8.6845
Average of Satisfaction Change 3 | Average of Effort Hours 768 | Average of Change Requests 1 | Average of Team Size 9

## 20 (hidden)
Budget | Cost
46300284.22 | 23114912.96

## 21 (hidden)
Status | Count
Completed | 17
In Progress | 157
Not Started | 13
Grand Total | 187

## 16 (hidden)
Project Type | Average of Percent Complete
Quality Improvement | 33.85%
Process Automation | 35.67%
Cybersecurity Hardening | 35.71%
EHR Upgrade | 39.13%
Equipment Procurement | 40.68%
Telehealth Rollout | 43.26%
New Wing Construction | 45.59%
Regulatory Compliance | 48.3%
Grand Total | 40.86%

## Sheet2 (hidden)
Count of Status | Column Labels
Project Type | Completed | In Progress | Not Started | Grand Total
Process Automation |  | 8 | 1 | 9
Cybersecurity Hardening |  | 11 |  | 11
Regulatory Compliance | 3 | 15 |  | 18
New Wing Construction | 2 | 19 | 1 | 22
Quality Improvement | 1 | 19 | 2 | 22
EHR Upgrade | 4 | 28 | 3 | 35
Telehealth Rollout | 4 | 28 | 4 | 36
Equipment Procurement | 3 | 29 | 2 | 34
Grand Total | 17 | 157 | 13 | 187

## Data
Project ID | Facility | Region | Department | Project Type | Priority | Status | PM Name | HER System | Start Date | End Date | Month | Duration Days | Tasks Completed | Tasks Total | Percent Complete | Budget | Cost | Change Requests | Scope Creep Score | Documentation Completeness | Effort Hours | Team Size | Readmission Rate Change Pct | Mortality Rate Change Pct | Satisfaction Change Pts
PRJ-2025-000028 | Al Noor Hospital | Upper Egypt | Cardiology | Quality Improvement | Medium | In Progress | Sarah Hassan | Allscripts | 2023-01-05 | 2023-01-16 | January | 11 | 8 | 36 | 22.22% | 69852.09 | 23050.81 | 1 | 10.8 | 13.1 | 1060.3 | 5 | -2.59 | -0.075 | 4.19
PRJ-2025-000040 | Al Noor Hospital | Upper Egypt | Surgery | EHR Upgrade | High | In Progress | Karim Ibrahim | Allscripts | 2023-01-28 | 2023-02-13 | January | 16 | 13 | 22 | 59.09% | 318853.89 | 132682.47 | 0 | 22.9 | 16.4 | 223.3 | 4 | -2.65 | 0.184 | -4.64
PRJ-2025-000074 | Riverbend Hospital | Nile Delta | Emergency | Regulatory Compliance | High | In Progress | Laila Ibrahim | Epic | 2023-01-24 | 2023-06-29 | January | 156 | 12 | 29 | 41.38% | 196405.94 | 46865.96 | 0 | 7.7 | 3.9 | 6770 | 5 | 1.19 | -0.317 | 6.28
PRJ-2025-003746 | Central Medical Center | Alexandria | ICU | Equipment Procurement | Critical | Completed | Youssef Ismail | Cerner | 2023-01-08 | 2023-01-28 | January | 20 | 13 | 13 | 100% | 400795.96 | 256220.36 | 2 | 93.4 | 53.5 | 1058.3 | 3 | -3.22 | -0.01 | 2.75
PRJ-2025-003826 | Central Medical Center | Nile Delta | Oncology | EHR Upgrade | High | In Progress | Farah Hamdy | Epic | 2023-01-08 | 2023-03-05 | January | 56 | 4 | 16 | 25% | 313519.04 | 214429.66 | 0 | 19.8 | 18.3 | 454.1 | 17 | -1.46 | 0.197 | -1.51
PRJ-2025-003878 | Riverbend Hospital | Nile Delta | OB/GYN | EHR Upgrade | High | In Progress | Laila Mostafa | Allscripts | 2023-01-13 | 2023-01-27 | January | 14 | 6 | 10 | 60% | 622413.56 | 511703.61 | 3 | 34.6 | 4.4 | 2426.4 | 3 | -0.38 | 0.323 | -3.97
PRJ-2025-003954 | Central Medical Center | Greater Cairo | Radiology | Process Automation | High | In Progress | Karim Ibrahim | Epic | 2023-01-30 | 2023-05-27 | January | 117 | 6 | 23 | 26.09% | 198852.81 | 8432.38 | 1 | 13.3 | 1.9 | 367.9 | 6 | 1.45 | 0.332 | 2.37
PRJ-2025-004001 | St. Mary’s Health | Greater Cairo | Surgery | Telehealth Rollout | Medium | In Progress | Farah Saleh | Cerner | 2023-01-12 | 2023-02-27 | January | 46 | 2 | 10 | 20% | 99372.65 | 74395.35 | 0 | 6.6 | 68.5 | 417.3 | 3 | -0.79 | 0.231 | 7.58
PRJ-2025-004020 | Central Medical Center | Upper Egypt | Emergency | Quality Improvement | Low | In Progress | Hany Mostafa | Cerner | 2023-01-08 | 2023-01-22 | January | 14 | 8 | 11 | 72.73% | 113986.33 | 48916.63 | 0 | 4.8 | 13.3 | 199.2 | 3 | -1.54 | 0.276 | 2.16
PRJ-2025-004607 | Riverbend Hospital | Alexandria | ICU | Telehealth Rollout | High | Completed | Hassan Mostafa | Cerner | 2023-01-08 | 2023-02-23 | January | 46 | 11 | 11 | 100% | 257805.29 | 296698.74 | 0 | 4 | 31 | 122.4 | 3 | -3.74 | -0.114 | 4
PRJ-2025-004633 | Riverbend Hospital | Alexandria | Pharmacy | Process Automation | High | In Progress | Ahmed Mostafa | Epic | 2023-01-04 | 2023-01-31 | January | 27 | 5 | 10 | 50% | 104793.43 | 1545.52 | 0 | 8.5 | 29.5 | 262.7 | 8 | -0.66 | -0.163 | -5.43
PRJ-2025-004646 | Green Valley Clinic | Sinai | Outpatient | EHR Upgrade | Critical | In Progress | Youssef Hamdy | Allscripts | 2023-01-27 | 2023-02-24 | January | 28 | 15 | 96 | 15.62% | 432258.07 | 162296.33 | 0 | 21.4 | 70.8 | 121.4 | 4 | -0.69 | 0.093 | 3.25
PRJ-2025-004871 | Al Noor Hospital | Alexandria | Radiology | Equipment Procurement | High | In Progress | Hany Younis | Allscripts | 2023-01-22 | 2023-03-13 | January | 50 | 8 | 16 | 50% | 580037.87 | 20809.84 | 0 | 9.6 | 15.1 | 1902.2 | 18 | 0.64 | 0.032 | 3.97
PRJ-2025-004913 | Al Noor Hospital | Alexandria | Radiology | Telehealth Rollout | Medium | In Progress | Amira Mahmoud | Epic | 2023-01-02 | 2023-04-03 | January | 91 | 15 | 20 | 75% | 126080.42 | 6807.14 | 0 | 50.2 | 8.3 | 402.7 | 3 | -1.06 | -0.209 | 3.08
PRJ-2025-004963 | Central Medical Center | Greater Cairo | Cardiology | Quality Improvement | High | In Progress | Laila Khaled | Epic | 2023-01-31 | 2023-02-28 | January | 28 | 5 | 13 | 38.46% | 256465.74 | 176153.38 | 1 | 4.8 | 27.6 | 908 | 3 | -1.81 | 0.139 | -4.72
PRJ-2025-004973 | Al Noor Hospital | Nile Delta | Oncology | Equipment Procurement | High | Not Started | Youssef Ismail | Epic | 2023-01-10 | 2023-01-29 | January | 19 | 0 | 10 | 0% | 115028.5 | 6540.99 | 4 | 14.8 | 28.8 | 300.3 | 4 | -0.27 | 0.007 | -1
PRJ-2025-005074 | Central Medical Center | Greater Cairo | Radiology | Quality Improvement | Critical | In Progress | Karim Ibrahim | Epic | 2023-01-17 | 2023-02-15 | January | 29 | 3 | 12 | 25% | 80936.15 | 58355.42 | 0 | 25 | 28.4 | 1802.2 | 3 | -0.2 | -0.361 | 8.28
PRJ-2025-005083 | Riverbend Hospital | Greater Cairo | Surgery | Quality Improvement | Low | In Progress | Farah Hassan | Cerner | 2023-01-26 | 2023-03-05 | January | 38 | 2 | 13 | 15.38% | 264378.58 | 191258.3 | 0 | 6.7 | 44.2 | 745.4 | 7 | -0.9 | -0.193 | -4.03
PRJ-2025-005136 | Al Noor Hospital | Upper Egypt | Emergency | Quality Improvement | Critical | Not Started | Ahmed Younis | Meditech | 2023-01-04 | 2023-02-09 | January | 36 | 0 | 41 | 0% | 1173108.47 | 68258.84 | 3 | 22.9 | 54.6 | 304.9 | 12 | -2.49 | -0.446 | 5.43
PRJ-2025-005191 | Central Medical Center | Alexandria | Emergency | Telehealth Rollout | High | In Progress | Karim Aziz | Meditech | 2023-01-18 | 2023-02-07 | January | 20 | 5 | 15 | 33.33% | 1260087.31 | 1012934.22 | 0 | 56 | 25.1 | 842.2 | 5 | 1.4 | -0.049 | 3.09
PRJ-2025-005247 | Green Valley Clinic | Upper Egypt | IM | EHR Upgrade | Medium | In Progress | Laila El Sayed | OpenMRS | 2023-01-10 | 2023-02-07 | January | 28 | 4 | 15 | 26.67% | 41843.19 | 1265.69 | 5 | 17.1 | 0.6 | 571.4 | 3 | -1.23 | -0.578 | -5.91
PRJ-2025-005284 | Sunrise Children’s | Greater Cairo | Emergency | Cybersecurity Hardening | Low | In Progress | Mona Ibrahim | OpenMRS | 2023-01-14 | 2023-03-06 | January | 51 | 14 | 25 | 56% | 33216.31 | 7287.17 | 1 | 20 | 5.9 | 829.9 | 4 | -1.47 | -0.071 | 6.38
PRJ-2025-005300 | Central Medical Center | Alexandria | Emergency | Equipment Procurement | High | Not Started | Ahmed Saleh | Cerner | 2023-01-12 | 2023-01-20 | January | 8 | 0 | 10 | 0% | 206538.23 | 16777.49 | 0 | 48.5 | 18.2 | 385.5 | 7 | 2.58 | 0.094 | 2.95
PRJ-2025-005324 | Eastside Cardio Institute | Nile Delta | ICU | Process Automation | Critical | Not Started | Laila Ibrahim | Allscripts | 2023-01-17 | 2023-01-26 | January | 9 | 0 | 55 | 0% | 176300.97 | 95703.32 | 3 | 15.4 | 30.7 | 257.6 | 16 | -0.11 | -0.174 | -4.65
PRJ-2025-005468 | Riverbend Hospital | Greater Cairo | ICU | EHR Upgrade | High | In Progress | Dina Saleh | Cerner | 2023-01-21 | 2023-02-04 | January | 14 | 2 | 11 | 18.18% | 128440.29 | 168635.73 | 6 | 5.3 | 24.3 | 336.3 | 18 | -1.01 | 0.295 | 3.06
PRJ-2025-005475 | Central Medical Center | Greater Cairo | IM | Regulatory Compliance | Medium | In Progress | Hany Mostafa | Allscripts | 2023-01-17 | 2023-03-08 | January | 50 | 23 | 58 | 39.66% | 391274.35 | 272482.65 | 2 | 3.5 | 22.1 | 1064.8 | 7 | -0.59 | -0.101 | 2.75
PRJ-2025-005510 | Al Noor Hospital | Alexandria | Surgery | EHR Upgrade | High | Completed | Dina Hassan | Cerner | 2023-01-22 | 2023-02-01 | January | 10 | 70 | 70 | 100% | 134886.49 | 119965.65 | 0 | 34.4 | 5.5 | 1947.8 | 23 | -1.65 | 0.192 | 2.83
PRJ-2025-005619 | St. Mary’s Health | Greater Cairo | IM | Cybersecurity Hardening | Critical | In Progress | Mona Hamdy | Cerner | 2023-01-28 | 2023-02-28 | January | 31 | 24 | 64 | 37.5% | 27494.7 | 24198.02 | 6 | 38.2 | 2.8 | 1714.1 | 7 | 0.2 | 0.266 | 3
PRJ-2025-005648 | Green Valley Clinic | Nile Delta | Surgery | Telehealth Rollout | Medium | In Progress | Laila Hassan | Epic | 2023-01-10 | 2023-01-26 | January | 16 | 12 | 34 | 35.29% | 82324.9 | 1266.52 | 2 | 8.9 | 12.5 | 537.6 | 4 | -1.06 | 0.261 | 2.57
PRJ-2025-005678 | Central Medical Center | Alexandria | Emergency | EHR Upgrade | High | In Progress | Tarek Mostafa | Epic | 2023-01-09 | 2023-02-17 | January | 39 | 3 | 10 | 30% | 60343.06 | 17290.68 | 0 | 71.7 | 44.4 | 913.8 | 4 | -0.12 | 0.065 | -3.13
PRJ-2025-005686 | Green Valley Clinic | Nile Delta | IM | Equipment Procurement | Low | Completed | Mona Ibrahim | Epic | 2023-01-22 | 2023-02-07 | January | 16 | 33 | 33 | 100% | 377835.02 | 85647.76 | 7 | 2.7 | 12.6 | 388.7 | 6 | -1.2 | -0.097 | 5.56
PRJ-2025-005688 | Sunrise Children’s | Upper Egypt | Surgery | EHR Upgrade | High | Not Started | Youssef Khaled | OpenMRS | 2023-01-30 | 2023-03-23 | January | 52 | 0 | 49 | 0% | 828997.13 | 1074051.26 | 1 | 17.4 | 26.4 | 1233.7 | 7 | 3.4 | -0.284 | 4.54
PRJ-2025-005732 | Al Noor Hospital | Greater Cairo | IM | New Wing Construction | Medium | In Progress | Ahmed Mostafa | Cerner | 2023-01-08 | 2023-05-16 | January | 128 | 1 | 17 | 5.882% | 606726.15 | 448765.11 | 2 | 13 | 7.1 | 2059.9 | 4 | -0.29 | 0.047 | -0.47
PRJ-2025-005776 | Al Noor Hospital | Greater Cairo | OB/GYN | New Wing Construction | High | In Progress | Sarah Khaled | Epic | 2023-01-13 | 2023-02-18 | January | 36 | 12 | 26 | 46.15% | 40541.15 | 26673.4 | 2 | 11.6 | 0.2 | 1386.1 | 17 | -3.1 | -0.073 | 6.83
PRJ-2025-005779 | Riverbend Hospital | Greater Cairo | Radiology | Quality Improvement | Low | In Progress | Hassan Farouk | Epic | 2023-01-26 | 2023-02-15 | January | 20 | 9 | 26 | 34.62% | 37338.15 | 25200.05 | 0 | 34.7 | 19.6 | 1604.5 | 12 | 1.75 | 0.058 | 1.91
PRJ-2025-005821 | Riverbend Hospital | Greater Cairo | Pharmacy | Equipment Procurement | Medium | In Progress | Hany Ismail | Epic | 2023-01-19 | 2023-02-25 | January | 37 | 7 | 21 | 33.33% | 20000 | 827.19 | 2 | 10.4 | 38.2 | 359.5 | 8 | 0.73 | -0.034 | 9.86
PRJ-2025-005840 | St. Mary’s Health | Upper Egypt | Oncology | Telehealth Rollout | Critical | In Progress | Youssef Khaled | Allscripts | 2023-01-09 | 2023-01-19 | January | 10 | 7 | 12 | 58.33% | 145071.52 | 103332.11 | 3 | 2.3 | 22.2 | 507.9 | 6 | 1 | 0.053 | 9.19
PRJ-2025-005885 | Al Noor Hospital | Red Sea | ICU | Process Automation | High | In Progress | Dina Ismail | Cerner | 2023-01-09 | 2023-02-09 | January | 31 | 5 | 13 | 38.46% | 130905.8 | 40456.24 | 0 | 4.7 | 16.5 | 475.8 | 21 | -2.62 | -0.155 | -1.7
PRJ-2025-005927 | Green Valley Clinic | Greater Cairo | Surgery | EHR Upgrade | High | In Progress | Dina Aziz | Epic | 2023-01-17 | 2023-02-17 | January | 31 | 6 | 37 | 16.22% | 703357.87 | 389418.36 | 1 | 12.9 | 1.2 | 2170.2 | 32 | 0.04 | 0.084 | 0.69
PRJ-2025-005994 | Al Noor Hospital | Nile Delta | Emergency | Telehealth Rollout | High | In Progress | Karim Khaled | Epic | 2023-01-29 | 2023-02-07 | January | 9 | 10 | 67 | 14.93% | 124805.89 | 76461.85 | 8 | 21.4 | 72.2 | 1405.9 | 3 | -0.49 | -0.144 | 5.67
PRJ-2025-005999 | Al Noor Hospital | Greater Cairo | IM | New Wing Construction | High | In Progress | Nadia Ismail | Allscripts | 2023-01-29 | 2023-02-06 | January | 8 | 37 | 64 | 57.81% | 156878.61 | 14543.09 | 0 | 34.5 | 64 | 608.8 | 25 | -0.85 | -0.38 | 4.95
PRJ-2025-006006 | Eastside Cardio Institute | Nile Delta | Oncology | Telehealth Rollout | Medium | In Progress | Omar Farouk | Cerner | 2023-01-22 | 2023-01-29 | January | 7 | 19 | 47 | 40.43% | 518308.76 | 86389.41 | 0 | 51.3 | 60.4 | 1157.9 | 3 | 1.84 | -0.04 | 12.26
PRJ-2025-006015 | Al Noor Hospital | Greater Cairo | Emergency | Cybersecurity Hardening | Low | In Progress | Amira Saleh | OpenMRS | 2023-01-16 | 2023-01-26 | January | 10 | 81 | 202 | 40.1% | 2013918.45 | 365159.03 | 0 | 9.5 | 2.1 | 607.6 | 3 | 0.09 | 0.071 | 8.79
PRJ-2025-006041 | St. Mary’s Health | Alexandria | Radiology | Cybersecurity Hardening | Medium | In Progress | Karim Mahmoud | Epic | 2023-01-28 | 2023-02-04 | January | 7 | 2 | 41 | 4.878% | 68424.24 | 27137.88 | 0 | 16.5 | 11.1 | 1805.4 | 3 | -3.65 | 0.169 | 2.89
PRJ-2025-006049 | Riverbend Hospital | Nile Delta | Outpatient | Equipment Procurement | Medium | In Progress | Tarek Mahmoud | Epic | 2023-01-19 | 2023-03-04 | January | 44 | 2 | 12 | 16.67% | 207594.16 | 97000.38 | 0 | 11.7 | 11.7 | 138.3 | 3 | 0.24 | 0.175 | -2.82
PRJ-2025-006092 | Green Valley Clinic | Upper Egypt | Emergency | Regulatory Compliance | High | Completed | Farah Ismail | Allscripts | 2023-01-22 | 2023-02-19 | January | 28 | 23 | 23 | 100% | 31854.27 | 6466.65 | 0 | 8.2 | 38.4 | 805.4 | 16 | 1.1 | -0.028 | 2.48
PRJ-2025-006182 | Central Medical Center | Greater Cairo | Orthopedics | Equipment Procurement | Low | In Progress | Laila Saleh | Epic | 2023-01-05 | 2023-01-29 | January | 24 | 5 | 18 | 27.78% | 103810.69 | 124532.33 | 13 | 6.5 | 5.7 | 152.1 | 5 | 0.74 | 0.124 | 2
PRJ-2025-006303 | Al Noor Hospital | Greater Cairo | Orthopedics | EHR Upgrade | Medium | Completed | Tarek Aziz | Cerner | 2023-01-16 | 2023-01-24 | January | 8 | 66 | 66 | 100% | 35906.36 | 41349.66 | 14 | 7.2 | 35.6 | 441 | 18 | 0.11 | 0.341 | 2.43
PRJ-2025-006420 | Al Noor Hospital | Upper Egypt | Oncology | Equipment Procurement | High | In Progress | Mona Aziz | Epic | 2023-01-29 | 2023-03-13 | January | 43 | 13 | 36 | 36.11% | 131233.72 | 1050.71 | 0 | 24.9 | 18.6 | 950.8 | 14 | -2.82 | 0.206 | 14.05
PRJ-2025-006426 | Central Medical Center | Red Sea | Pediatrics | EHR Upgrade | High | In Progress | Amira Younis | Cerner | 2023-01-09 | 2023-02-12 | January | 34 | 6 | 24 | 25% | 439242.27 | 259183.11 | 2 | 15.6 | 15.1 | 920.6 | 4 | 0.82 | 0.054 | 1.64
PRJ-2025-006467 | Al Noor Hospital | Greater Cairo | Emergency | New Wing Construction | High | In Progress | Farah Farouk | Epic | 2023-01-29 | 2023-04-05 | January | 66 | 8 | 14 | 57.14% | 217091.3 | 168215.24 | 6 | 23.3 | 12.4 | 2214.3 | 3 | -0.74 | -0.314 | 9.24
PRJ-2025-006514 | Green Valley Clinic | Greater Cairo | Surgery | New Wing Construction | High | In Progress | Laila Younis | Cerner | 2023-01-07 | 2023-04-05 | January | 88 | 20 | 29 | 68.97% | 168522.83 | 63451.5 | 0 | 4.3 | 18.2 | 417.2 | 25 | -1.46 | -0.09 | 3.19
PRJ-2025-006557 | Al Noor Hospital | Greater Cairo | Emergency | Cybersecurity Hardening | Medium | In Progress | Laila Hamdy | OpenMRS | 2023-01-31 | 2023-02-15 | January | 15 | 11 | 21 | 52.38% | 21838.67 | 10155.2 | 3 | 28.2 | 10.7 | 1407.8 | 3 | 1.31 | -0.41 | 5
PRJ-2025-006574 | Sunrise Children’s | Greater Cairo | Emergency | Cybersecurity Hardening | Medium | In Progress | Amira Ismail | Cerner | 2023-01-28 | 2023-02-10 | January | 13 | 3 | 12 | 25% | 501973.2 | 225074.92 | 2 | 15 | 15.6 | 159.4 | 7 | -1.37 | -0.272 | 5.94
PRJ-2025-006578 | Central Medical Center | Nile Delta | IM | Equipment Procurement | High | In Progress | Sarah Hamdy | Cerner | 2023-01-17 | 2023-03-30 | January | 72 | 7 | 15 | 46.67% | 165549.72 | 83121.95 | 2 | 46.3 | 6 | 752.9 | 3 | -0.05 | 0.157 | 4.12
PRJ-2025-006588 | Central Medical Center | Greater Cairo | Cardiology | EHR Upgrade | Medium | In Progress | Ahmed Ismail | Allscripts | 2023-01-23 | 2023-02-19 | January | 27 | 5 | 16 | 31.25% | 40660.46 | 2642.02 | 0 | 14.1 | 2.9 | 1234 | 4 | -0.85 | 0.065 | 2.38
PRJ-2025-006634 | Al Noor Hospital | Nile Delta | Emergency | Quality Improvement | High | In Progress | Nadia El Sayed | OpenMRS | 2023-01-18 | 2023-02-01 | January | 14 | 2 | 12 | 16.67% | 339360.72 | 178567.43 | 0 | 13.8 | 9 | 491.8 | 3 | 0.03 | -0.213 | 7.35
PRJ-2025-006687 | Al Noor Hospital | Alexandria | Emergency | Telehealth Rollout | High | In Progress | Sarah Ibrahim | Meditech | 2023-01-19 | 2023-03-07 | January | 47 | 33 | 84 | 39.29% | 40022.58 | 12929.88 | 0 | 26.6 | 4.9 | 449.7 | 4 | 0.39 | 0.183 | 2.85
PRJ-2025-006707 | Sunrise Children’s | Upper Egypt | Pharmacy | Equipment Procurement | Medium | In Progress | Sarah El Sayed | Epic | 2023-01-24 | 2023-02-03 | January | 10 | 16 | 23 | 69.57% | 310916.49 | 336937.68 | 0 | 11.6 | 19.5 | 294.8 | 12 | -3.78 | -0.065 | 3.63
PRJ-2025-006710 | Sunrise Children’s | Sinai | ICU | Equipment Procurement | Critical | In Progress | Hany Ibrahim | Cerner | 2023-01-28 | 2023-03-01 | January | 32 | 4 | 21 | 19.05% | 1078796.7 | 894932.48 | 4 | 4.6 | 42.2 | 387.4 | 3 | -1.53 | -0.201 | 10.65
PRJ-2025-006715 | Riverbend Hospital | Upper Egypt | Pediatrics | New Wing Construction | High | In Progress | Sarah Mahmoud | Epic | 2023-01-24 | 2023-02-03 | January | 10 | 5 | 13 | 38.46% | 67293.67 | 11614.53 | 0 | 14.9 | 10.9 | 318.6 | 11 | 0.35 | 0.097 | 6.77
PRJ-2025-006774 | Central Medical Center | Greater Cairo | IM | New Wing Construction | High | In Progress | Youssef Younis | Cerner | 2023-01-04 | 2023-01-20 | January | 16 | 2 | 11 | 18.18% | 504764.19 | 48175.53 | 0 | 13.2 | 17.8 | 126.8 | 14 | -2.57 | -0.162 | 3.15
PRJ-2025-006794 | Central Medical Center | Nile Delta | Orthopedics | New Wing Construction | High | In Progress | Tarek Aziz | Allscripts | 2023-01-01 | 2023-01-14 | January | 13 | 9 | 26 | 34.62% | 129041.57 | 86880.6 | 0 | 41 | 54.9 | 551.3 | 26 | -2.12 | -0.257 | -4.08
PRJ-2025-006813 | Central Medical Center | Greater Cairo | Surgery | Quality Improvement | High | In Progress | Mona Ibrahim | Cerner | 2023-01-18 | 2023-03-09 | January | 50 | 4 | 14 | 28.57% | 128720.38 | 113085.91 | 0 | 27.6 | 0.3 | 1290.6 | 3 | 1.41 | 0.157 | -1.33
PRJ-2025-006838 | St. Mary’s Health | Greater Cairo | Surgery | Telehealth Rollout | High | Not Started | Tarek Saleh | Epic | 2023-01-11 | 2023-01-24 | January | 13 | 0 | 15 | 0% | 170065.66 | 139154.75 | 0 | 46.7 | 9.9 | 1925.7 | 8 | 0.94 | -0.339 | 7.21
PRJ-2025-006878 | Central Medical Center | Greater Cairo | Pediatrics | New Wing Construction | High | Completed | Ahmed Hassan | OpenMRS | 2023-01-26 | 2023-02-06 | January | 11 | 10 | 10 | 100% | 279610.4 | 160313.61 | 0 | 15.2 | 52.5 | 375 | 4 | -0.29 | -0.122 | 8.49
PRJ-2025-006933 | Al Noor Hospital | Greater Cairo | Emergency | Quality Improvement | Low | In Progress | Hany Younis | Cerner | 2023-01-06 | 2023-01-13 | January | 7 | 4 | 12 | 33.33% | 469221.36 | 42481.79 | 3 | 3.7 | 30.3 | 1019.7 | 3 | 0.34 | 0.08 | 7.59
PRJ-2025-006977 | Green Valley Clinic | Greater Cairo | Emergency | Telehealth Rollout | High | In Progress | Farah Younis | Epic | 2023-01-07 | 2023-01-17 | January | 10 | 3 | 14 | 21.43% | 147957.93 | 168759.16 | 0 | 89 | 10.5 | 284.2 | 9 | -0.87 | -0.054 | 9.66
PRJ-2025-006982 | Al Noor Hospital | Alexandria | IM | Process Automation | High | In Progress | Amira Aziz | Epic | 2023-01-11 | 2023-02-06 | January | 26 | 21 | 32 | 65.62% | 112264.36 | 113924.22 | 0 | 12.6 | 20.7 | 225.8 | 5 | 2.44 | 0.125 | 1.8
PRJ-2025-007062 | Al Noor Hospital | Upper Egypt | Surgery | Telehealth Rollout | Medium | In Progress | Farah Saleh | Cerner | 2023-01-18 | 2023-01-25 | January | 7 | 4 | 23 | 17.39% | 72895.66 | 36054.29 | 4 | 36.5 | 14.3 | 208.1 | 4 | -0.9 | -0.23 | -0.53
PRJ-2025-007192 | Al Noor Hospital | Alexandria | Emergency | EHR Upgrade | High | In Progress | Sarah Younis | Cerner | 2023-01-21 | 2023-05-24 | January | 123 | 3 | 56 | 5.357% | 44090.31 | 15659.51 | 8 | 8.4 | 24.6 | 470 | 6 | 2.35 | 0.016 | -10.47
PRJ-2025-000012 | Eastside Cardio Institute | Alexandria | Emergency | Regulatory Compliance | Medium | In Progress | Nadia Younis | Cerner | 2023-02-16 | 2023-03-02 | February | 14 | 2 | 12 | 16.67% | 81435.58 | 30557.14 | 4 | 4.2 | 27 | 371.3 | 3 | -1.44 | 0.293 | 2.03
PRJ-2025-000063 | Riverbend Hospital | Upper Egypt | Emergency | Quality Improvement | Critical | In Progress | Omar Hassan | Cerner | 2023-02-18 | 2023-03-12 | February | 22 | 6 | 13 | 46.15% | 152177.11 | 111101.69 | 1 | 10.1 | 11.9 | 336.8 | 3 | -1.13 | -0.122 | 3.18
PRJ-2025-000110 | Central Medical Center | Greater Cairo | Emergency | EHR Upgrade | Critical | In Progress | Nadia Ibrahim | Cerner | 2023-02-21 | 2023-03-19 | February | 26 | 30 | 37 | 81.08% | 710084.43 | 666779.13 | 0 | 11.1 | 48.1 | 737.3 | 6 | -0.88 | -0.113 | -2.47
PRJ-2025-003853 | St. Mary’s Health | Greater Cairo | Emergency | Equipment Procurement | High | In Progress | Laila Saleh | Allscripts | 2023-02-09 | 2023-03-27 | February | 46 | 13 | 16 | 81.25% | 32750.92 | 4863.12 | 0 | 23.4 | 27.9 | 214.1 | 21 | 1 | 0.328 | 8.5
PRJ-2025-003883 | Eastside Cardio Institute | Greater Cairo | Cardiology | EHR Upgrade | Low | Completed | Farah Younis | Allscripts | 2023-02-14 | 2023-05-07 | February | 82 | 11 | 11 | 100% | 101961.56 | 59201.46 | 0 | 47.1 | 79.1 | 935.3 | 20 | -2.24 | -0.163 | 6.06
PRJ-2025-004595 | Al Noor Hospital | Greater Cairo | Surgery | Telehealth Rollout | High | In Progress | Amira Aziz | Epic | 2023-02-20 | 2023-02-27 | February | 7 | 3 | 16 | 18.75% | 249886.22 | 11808.01 | 1 | 1.6 | 43.9 | 295.3 | 3 | -1.06 | -0.052 | 0.14
PRJ-2025-004742 | Central Medical Center | Upper Egypt | Surgery | Cybersecurity Hardening | Critical | In Progress | Farah Mostafa | Epic | 2023-02-19 | 2023-03-18 | February | 27 | 5 | 11 | 45.45% | 28553.19 | 2004.9 | 0 | 13.8 | 21.3 | 426.9 | 4 | -0.92 | 0.148 | -0.07
PRJ-2025-004752 | Al Noor Hospital | Nile Delta | Emergency | Telehealth Rollout | High | In Progress | Ahmed Ismail | Epic | 2023-02-27 | 2023-03-21 | February | 22 | 11 | 23 | 47.83% | 111266.82 | 7917.69 | 2 | 22 | 15.3 | 388.5 | 3 | -0.11 | 0.147 | -0.14
PRJ-2025-004792 | Eastside Cardio Institute | Greater Cairo | IM | Telehealth Rollout | Medium | In Progress | Hassan Ismail | Meditech | 2023-02-03 | 2023-05-19 | February | 105 | 3 | 12 | 25% | 122736.75 | 82997.1 | 0 | 4.7 | 3.2 | 322.3 | 3 | -1.42 | 0.076 | -3.21
PRJ-2025-004852 | Al Noor Hospital | Upper Egypt | Surgery | Telehealth Rollout | High | In Progress | Mona Mahmoud | Cerner | 2023-02-06 | 2023-03-14 | February | 36 | 49 | 79 | 62.03% | 108022.4 | 35109.51 | 2 | 40.6 | 14.3 | 322.1 | 200 | -0.61 | -0.045 | -8.7
PRJ-2025-004866 | St. Mary’s Health | Greater Cairo | Radiology | EHR Upgrade | High | In Progress | Laila Mahmoud | Cerner | 2023-02-04 | 2023-02-26 | February | 22 | 2 | 10 | 20% | 99658.32 | 53975.12 | 1 | 55.3 | 15.2 | 82.1 | 3 | -0.36 | -0.256 | 8.61
PRJ-2025-004868 | Central Medical Center | Upper Egypt | Oncology | New Wing Construction | High | In Progress | Karim Hassan | Meditech | 2023-02-27 | 2023-04-16 | February | 48 | 22 | 34 | 64.71% | 178392.22 | 113695.6 | 2 | 2.9 | 3 | 617.1 | 5 | -0.92 | -0.077 | 4.8
PRJ-2025-004977 | Central Medical Center | Alexandria | Emergency | Regulatory Compliance | High | In Progress | Youssef Saleh | Epic | 2023-02-26 | 2023-03-12 | February | 14 | 4 | 15 | 26.67% | 466944.46 | 467484.47 | 1 | 12.8 | 8.5 | 306.5 | 4 | -1.39 | -0.071 | 0.03
PRJ-2025-004994 | St. Mary’s Health | Alexandria | IM | Equipment Procurement | High | In Progress | Hany Mostafa | Epic | 2023-02-20 | 2023-03-14 | February | 22 | 20 | 70 | 28.57% | 79877.62 | 40679.08 | 0 | 20.5 | 12.3 | 853.7 | 3 | -0.64 | -0.209 | 2.33
PRJ-2025-005021 | St. Mary’s Health | Nile Delta | Surgery | Telehealth Rollout | High | Completed | Karim Hassan | Cerner | 2023-02-07 | 2023-02-14 | February | 7 | 14 | 14 | 100% | 427198.35 | 66753.31 | 1 | 9.6 | 31.8 | 745.7 | 6 | 0.45 | 0.109 | 9.96
PRJ-2025-005044 | St. Mary’s Health | Nile Delta | Surgery | Regulatory Compliance | Medium | In Progress | Youssef Saleh | Allscripts | 2023-02-11 | 2023-02-20 | February | 9 | 5 | 11 | 45.45% | 130249.01 | 155686.65 | 8 | 93.7 | 6.3 | 1153 | 12 | 2.03 | -0.622 | -2.83
PRJ-2025-005145 | Al Noor Hospital | Sinai | Cardiology | Equipment Procurement | Medium | In Progress | Youssef Younis | Epic | 2023-02-25 | 2023-03-09 | February | 12 | 3 | 12 | 25% | 593143.55 | 159181.87 | 0 | 71.6 | 60.4 | 169.9 | 5 | -0.7 | 0.226 | 10.56
PRJ-2025-005243 | Al Noor Hospital | Alexandria | Outpatient | Regulatory Compliance | High | In Progress | Farah Mostafa | Epic | 2023-02-01 | 2023-02-16 | February | 15 | 12 | 18 | 66.67% | 170117.58 | 125997.9 | 0 | 31.9 | 1.6 | 374.4 | 4 | -0.45 | 0.147 | 3.53
PRJ-2025-005381 | Central Medical Center | Greater Cairo | Oncology | Regulatory Compliance | Medium | In Progress | Dina Younis | Meditech | 2023-02-05 | 2023-02-12 | February | 7 | 12 | 30 | 40% | 93183.36 | 18226.49 | 0 | 27.7 | 28.4 | 401.9 | 13 | -2.03 | 0.205 | 5.19
PRJ-2025-005409 | Central Medical Center | Greater Cairo | Radiology | Telehealth Rollout | Critical | In Progress | Mona Mahmoud | Allscripts | 2023-02-27 | 2023-04-17 | February | 49 | 3 | 10 | 30% | 240274.18 | 129391.22 | 0 | 19.6 | 37 | 157.3 | 35 | -0.94 | 0.042 | 3.89
PRJ-2025-005520 | St. Mary’s Health | Greater Cairo | IM | Quality Improvement | Medium | Completed | Ahmed Saleh | Cerner | 2023-02-21 | 2023-03-30 | February | 37 | 20 | 20 | 100% | 113763.96 | 6486.95 | 0 | 4.3 | 62.8 | 955.1 | 10 | 0.62 | -0.42 | 8.75
PRJ-2025-005569 | Riverbend Hospital | Alexandria | Surgery | Telehealth Rollout | Medium | In Progress | Youssef Aziz | Allscripts | 2023-02-26 | 2023-05-07 | February | 70 | 9 | 19 | 47.37% | 64436.72 | 44657.95 | 3 | 22.2 | 12 | 332.5 | 5 | -1.16 | 0.077 | 6.26
PRJ-2025-005668 | Riverbend Hospital | Alexandria | IM | Equipment Procurement | Critical | In Progress | Laila Ismail | Epic | 2023-02-18 | 2023-02-28 | February | 10 | 85 | 417 | 20.38% | 28827.69 | 14528.88 | 0 | 3.3 | 35.6 | 1719.5 | 10 | -0.73 | -0.207 | -0.14
PRJ-2025-005702 | Al Noor Hospital | Greater Cairo | Surgery | New Wing Construction | Medium | In Progress | Farah Mostafa | Cerner | 2023-02-18 | 2023-03-02 | February | 12 | 14 | 32 | 43.75% | 173571.68 | 32929.28 | 1 | 30.4 | 51.2 | 429 | 6 | 0.43 | -0.1 | 1.49
PRJ-2025-005733 | St. Mary’s Health | Alexandria | IM | Telehealth Rollout | High | In Progress | Sarah El Sayed | Epic | 2023-02-20 | 2023-03-01 | February | 9 | 10 | 28 | 35.71% | 133489.68 | 82985.1 | 0 | 7.3 | 6.9 | 1259.7 | 4 | 0.43 | 0.039 | 1.6
PRJ-2025-005744 | Eastside Cardio Institute | Greater Cairo | Outpatient | Telehealth Rollout | Medium | In Progress | Tarek Farouk | Meditech | 2023-02-06 | 2023-02-17 | February | 11 | 52 | 74 | 70.27% | 92745.7 | 47708.47 | 2 | 13.2 | 27.1 | 357.3 | 3 | -2.24 | 0.282 | 6.04
PRJ-2025-005793 | Eastside Cardio Institute | Alexandria | Oncology | New Wing Construction | High | In Progress | Hassan Khaled | Epic | 2023-02-15 | 2023-03-09 | February | 22 | 20 | 90 | 22.22% | 1023035.14 | 171749.15 | 4 | 38 | 6.5 | 1615.9 | 5 | -1.77 | -0.008 | -1.9
PRJ-2025-005827 | St. Mary’s Health | Greater Cairo | ID | New Wing Construction | High | In Progress | Dina Farouk | Epic | 2023-02-17 | 2023-03-01 | February | 12 | 7 | 13 | 53.85% | 34187.01 | 25761.63 | 0 | 9.4 | 8.1 | 1649.6 | 17 | -2.17 | -0.045 | 1.64
PRJ-2025-005837 | Sunrise Children’s | Nile Delta | Surgery | Cybersecurity Hardening | Medium | In Progress | Hassan Aziz | Cerner | 2023-02-02 | 2023-02-09 | February | 7 | 8 | 17 | 47.06% | 107271.61 | 36725.95 | 5 | 7.6 | 20.1 | 83.5 | 30 | -0.27 | -0.25 | 4.41
PRJ-2025-005856 | Green Valley Clinic | Nile Delta | Surgery | Regulatory Compliance | Medium | In Progress | Ahmed Mahmoud | Epic | 2023-02-04 | 2023-02-18 | February | 14 | 46 | 162 | 28.4% | 227297.61 | 212280.44 | 0 | 21.8 | 5.9 | 832.1 | 13 | -0.56 | 0.027 | -4.73
PRJ-2025-005857 | Central Medical Center | Greater Cairo | IM | Process Automation | Medium | In Progress | Omar Saleh | Epic | 2023-02-26 | 2023-03-13 | February | 15 | 8 | 40 | 20% | 122012.43 | 33634.87 | 0 | 4.3 | 18.3 | 493.8 | 17 | 0.71 | 0.267 | -1.4
PRJ-2025-005949 | St. Mary’s Health | Upper Egypt | Emergency | EHR Upgrade | Critical | In Progress | Mona Younis | Cerner | 2023-02-01 | 2023-02-23 | February | 22 | 21 | 42 | 50% | 50704.07 | 16736.37 | 0 | 51.8 | 69.7 | 454.3 | 5 | -1.3 | 0.118 | 8.88
PRJ-2025-006014 | Al Noor Hospital | Greater Cairo | Emergency | Quality Improvement | Medium | In Progress | Farah Saleh | Cerner | 2023-02-24 | 2023-05-26 | February | 91 | 29 | 73 | 39.73% | 233284.17 | 98829.74 | 0 | 15.5 | 19.2 | 235.7 | 14 | -0.44 | 0.022 | -7.12
PRJ-2025-006065 | Central Medical Center | Alexandria | Oncology | Telehealth Rollout | High | In Progress | Farah Ismail | Cerner | 2023-02-01 | 2023-02-11 | February | 10 | 56 | 73 | 76.71% | 204157.24 | 42656.35 | 2 | 41.2 | 12.1 | 98.2 | 3 | -2.3 | -0.207 | -3.45
PRJ-2025-006111 | Eastside Cardio Institute | Greater Cairo | Pharmacy | Equipment Procurement | High | In Progress | Dina Hassan | Cerner | 2023-02-02 | 2023-03-31 | February | 57 | 310 | 500 | 62% | 33613.65 | 30276.78 | 2 | 54.2 | 32.8 | 236.4 | 5 | 0.23 | 0.259 | 12.63
PRJ-2025-006284 | Green Valley Clinic | Greater Cairo | Orthopedics | EHR Upgrade | High | In Progress | Laila El Sayed | Cerner | 2023-02-28 | 2023-03-28 | February | 28 | 10 | 14 | 71.43% | 58643.86 | 19655.34 | 1 | 12.7 | 13.7 | 706.7 | 11 | 1.15 | -0.38 | 5.64
PRJ-2025-006295 | Riverbend Hospital | Greater Cairo | Pediatrics | Equipment Procurement | High | In Progress | Hassan Saleh | Epic | 2023-02-18 | 2023-03-17 | February | 27 | 2 | 10 | 20% | 137619.58 | 90178.42 | 0 | 19.9 | 23.4 | 388 | 15 | 1.64 | -0.413 | 3.61
PRJ-2025-006298 | Central Medical Center | Greater Cairo | Surgery | Telehealth Rollout | Critical | In Progress | Farah Khaled | Allscripts | 2023-02-27 | 2023-04-06 | February | 38 | 28 | 39 | 71.79% | 213635.91 | 188116.02 | 0 | 21.1 | 23.3 | 377.9 | 10 | -0.63 | 0.109 | 7.76
PRJ-2025-006309 | Al Noor Hospital | Greater Cairo | Outpatient | New Wing Construction | Critical | In Progress | Karim Aziz | Cerner | 2023-02-16 | 2023-03-15 | February | 27 | 6 | 19 | 31.58% | 171425.21 | 231048.44 | 1 | 31.3 | 32.2 | 414.1 | 5 | -0.78 | -0.25 | -1.35
PRJ-2025-006372 | Central Medical Center | Greater Cairo | Orthopedics | Equipment Procurement | High | In Progress | Sarah Farouk | Allscripts | 2023-02-01 | 2023-03-08 | February | 35 | 141 | 500 | 28.2% | 181885.58 | 91818.31 | 1 | 40.6 | 5.5 | 274 | 9 | 1.84 | 0.264 | 11.33
PRJ-2025-006414 | Al Noor Hospital | Nile Delta | Radiology | Equipment Procurement | Critical | In Progress | Omar El Sayed | Allscripts | 2023-02-10 | 2023-03-18 | February | 36 | 15 | 36 | 41.67% | 561832.12 | 642395.73 | 1 | 15.2 | 4.9 | 174.8 | 3 | -3.44 | 0.114 | 1.92
PRJ-2025-006437 | St. Mary’s Health | Greater Cairo | Oncology | Telehealth Rollout | Low | In Progress | Hassan Saleh | Cerner | 2023-02-19 | 2023-03-11 | February | 20 | 145 | 500 | 29% | 74197.85 | 75482.96 | 0 | 3.8 | 69.4 | 155.9 | 17 | -0.22 | 0.024 | 0.42
PRJ-2025-006477 | Al Noor Hospital | Greater Cairo | Surgery | Equipment Procurement | High | In Progress | Hany Ismail | Epic | 2023-02-17 | 2023-04-11 | February | 53 | 6 | 13 | 46.15% | 80169.45 | 111724.94 | 0 | 15.1 | 52.1 | 2450.2 | 3 | -2.28 | -0.025 | 6.6
PRJ-2025-006501 | Central Medical Center | Greater Cairo | Surgery | Regulatory Compliance | Medium | In Progress | Omar Ismail | Allscripts | 2023-02-08 | 2023-03-17 | February | 37 | 3 | 18 | 16.67% | 411819.57 | 22132.76 | 3 | 10.9 | 3.4 | 439.8 | 9 | 0.8 | 0.168 | -1.14
PRJ-2025-006542 | Riverbend Hospital | Nile Delta | IM | Quality Improvement | High | In Progress | Ahmed Mostafa | Epic | 2023-02-12 | 2023-03-01 | February | 17 | 4 | 13 | 30.77% | 289294.37 | 13586.1 | 1 | 7 | 9.7 | 502.4 | 3 | -2.46 | 0.216 | 1.31
PRJ-2025-006606 | Central Medical Center | Nile Delta | Orthopedics | Telehealth Rollout | Critical | In Progress | Karim Younis | Epic | 2023-02-26 | 2023-03-23 | February | 25 | 5 | 22 | 22.73% | 97484.91 | 6102.64 | 4 | 14.1 | 23 | 455.8 | 3 | -0.88 | 0.194 | 5.38
PRJ-2025-006612 | Green Valley Clinic | Upper Egypt | Pharmacy | EHR Upgrade | High | Completed | Youssef Saleh | Epic | 2023-02-22 | 2023-03-01 | February | 7 | 27 | 27 | 100% | 723433.97 | 551865.75 | 5 | 12.5 | 57.2 | 588.2 | 5 | 1.51 | 0.132 | 7.43
PRJ-2025-006635 | St. Mary’s Health | Greater Cairo | Surgery | Telehealth Rollout | Critical | In Progress | Sarah Younis | Cerner | 2023-02-01 | 2023-03-14 | February | 41 | 130 | 178 | 73.03% | 253173.15 | 318843.43 | 0 | 26.7 | 54.5 | 450.2 | 4 | 0.45 | 0.16 | 3.67
PRJ-2025-006652 | Riverbend Hospital | Alexandria | Cardiology | Regulatory Compliance | Medium | In Progress | Youssef Khaled | Epic | 2023-02-07 | 2023-03-08 | February | 29 | 6 | 12 | 50% | 435572.35 | 362523.04 | 0 | 13 | 3.5 | 622.4 | 3 | -0.95 | 0.02 | -0.49
PRJ-2025-006671 | Central Medical Center | Upper Egypt | IM | EHR Upgrade | Medium | In Progress | Hassan Ismail | OpenMRS | 2023-02-02 | 2023-02-17 | February | 15 | 4 | 10 | 40% | 737344.81 | 288067.39 | 2 | 10 | 14 | 356.6 | 5 | -1.79 | 0.128 | 4.19
PRJ-2025-006740 | Sunrise Children’s | Greater Cairo | Emergency | Regulatory Compliance | Critical | In Progress | Farah Hassan | Cerner | 2023-02-22 | 2023-05-04 | February | 71 | 3 | 10 | 30% | 99287.23 | 65446.52 | 4 | 98.6 | 13.9 | 670.4 | 4 | -3.38 | -0.023 | 0.91
PRJ-2025-006793 | Al Noor Hospital | Greater Cairo | Surgery | New Wing Construction | Medium | In Progress | Hassan El Sayed | Cerner | 2023-02-15 | 2023-03-03 | February | 16 | 35 | 59 | 59.32% | 138662.37 | 52663.98 | 1 | 23.9 | 6.4 | 1696 | 4 | -1.22 | -0.231 | 5.76
PRJ-2025-007024 | Green Valley Clinic | Red Sea | Pediatrics | Telehealth Rollout | Medium | Not Started | Ahmed Ismail | Epic | 2023-02-17 | 2023-04-07 | February | 49 | 0 | 78 | 0% | 84565.09 | 78768.09 | 0 | 22.8 | 4.9 | 456 | 3 | -2.16 | 0.103 | 2.52
PRJ-2025-007042 | Al Noor Hospital | Greater Cairo | Cardiology | Cybersecurity Hardening | Medium | In Progress | Hany Mostafa | Cerner | 2023-02-02 | 2023-03-16 | February | 42 | 38 | 74 | 51.35% | 182303.81 | 179217.87 | 0 | 8 | 8.5 | 675 | 6 | -0.88 | -0.017 | -0.73
PRJ-2025-007066 | St. Mary’s Health | Greater Cairo | Surgery | Regulatory Compliance | High | In Progress | Youssef Khaled | Epic | 2023-02-24 | 2023-04-16 | February | 51 | 28 | 67 | 41.79% | 98658.69 | 128825.88 | 1 | 8.9 | 23.4 | 631.6 | 29 | -1.53 | 0.202 | -3.59
PRJ-2025-007165 | Green Valley Clinic | Greater Cairo | Emergency | EHR Upgrade | High | In Progress | Laila Farouk | Epic | 2023-02-17 | 2023-03-03 | February | 14 | 8 | 17 | 47.06% | 208144.33 | 161035.4 | 3 | 2.6 | 17.9 | 1633.9 | 6 | 0.98 | 0.105 | 0.95
PRJ-2025-000003 | Green Valley Clinic | Alexandria | Oncology | Process Automation | Low | In Progress | Mona Khaled | Cerner | 2023-03-02 | 2023-03-18 | March | 16 | 3 | 18 | 16.67% | 388047.36 | 126596.22 | 2 | 40.4 | 22.7 | 179.1 | 3 | -2.44 | 0.469 | -1.8
PRJ-2025-000047 | Central Medical Center | Greater Cairo | Emergency | EHR Upgrade | Medium | Not Started | Ahmed El Sayed | Allscripts | 2023-03-26 | 2023-04-02 | March | 7 | 0 | 21 | 0% | 1189947.65 | 200889.44 | 0 | 100 | 40 | 2160.6 | 5 | 0.47 | -0.193 | -3.2
PRJ-2025-003754 | St. Mary’s Health | Greater Cairo | Emergency | Process Automation | Medium | In Progress | Amira Farouk | Epic | 2023-03-14 | 2023-05-06 | March | 53 | 14 | 16 | 87.5% | 123179.19 | 68091.9 | 0 | 30.3 | 4.7 | 1034.2 | 6 | 1.28 | -0.012 | 1.77
PRJ-2025-003769 | Central Medical Center | Alexandria | Radiology | Telehealth Rollout | Medium | Completed | Omar El Sayed | Cerner | 2023-03-09 | 2023-04-08 | March | 30 | 10 | 10 | 100% | 86484 | 28907.94 | 0 | 18.1 | 20.9 | 993.2 | 5 | -4.56 | -0.169 | 2.94
PRJ-2025-003926 | Central Medical Center | Greater Cairo | Surgery | Quality Improvement | Critical | In Progress | Nadia Ibrahim | Allscripts | 2023-03-31 | 2023-04-07 | March | 7 | 17 | 59 | 28.81% | 501963.1 | 541861.39 | 0 | 25.3 | 27 | 301.5 | 7 | 0.3 | -0.15 | 6.46
PRJ-2025-003969 | St. Mary’s Health | Upper Egypt | IM | Equipment Procurement | Critical | In Progress | Youssef Younis | Cerner | 2023-03-27 | 2023-07-22 | March | 117 | 5 | 13 | 38.46% | 57969.83 | 58602.9 | 7 | 4.1 | 20.1 | 120.7 | 3 | 0.98 | -0.328 | 0.95
PRJ-2025-004008 | Al Noor Hospital | Nile Delta | Cardiology | New Wing Construction | Critical | In Progress | Mona Farouk | OpenMRS | 2023-03-21 | 2023-04-08 | March | 18 | 14 | 22 | 63.64% | 53481.75 | 16237.55 | 0 | 15.7 | 28.8 | 238.9 | 3 | 0.89 | 0.048 | 2.43
PRJ-2025-004022 | Central Medical Center | Greater Cairo | ICU | EHR Upgrade | High | In Progress | Hassan Aziz | Cerner | 2023-03-07 | 2023-04-07 | March | 31 | 7 | 18 | 38.89% | 153028.39 | 116402.88 | 1 | 10.7 | 56.1 | 932.7 | 6 | -1.3 | 0.326 | 5.91
PRJ-2025-004611 | Central Medical Center | Greater Cairo | Emergency | Quality Improvement | Critical | In Progress | Amira Saleh | Cerner | 2023-03-22 | 2023-04-21 | March | 30 | 5 | 14 | 35.71% | 94659.38 | 45820.35 | 0 | 37.8 | 18 | 507.2 | 7 | 0.3 | -0.091 | 4.26
PRJ-2025-004618 | Riverbend Hospital | Greater Cairo | Surgery | Equipment Procurement | High | In Progress | Amira Mostafa | Meditech | 2023-03-19 | 2023-11-24 | March | 250 | 56 | 111 | 50.45% | 156238.98 | 54510.53 | 2 | 19.9 | 56.4 | 626.3 | 3 | -0.48 | 0.148 | 8.65
PRJ-2025-004625 | Sunrise Children’s | Upper Egypt | Emergency | Equipment Procurement | High | Completed | Omar Mahmoud | Meditech | 2023-03-03 | 2023-04-15 | March | 43 | 17 | 17 | 100% | 321282.49 | 106550.34 | 0 | 18.7 | 3.2 | 476 | 3 | -0.27 | 0.138 | 0.5
PRJ-2025-004650 | Central Medical Center | Greater Cairo | Emergency | EHR Upgrade | High | In Progress | Omar Farouk | Allscripts | 2023-03-21 | 2023-04-06 | March | 16 | 3 | 17 | 17.65% | 116839.91 | 83457 | 0 | 10.8 | 37.4 | 250.9 | 55 | 1.62 | -0.203 | -0.4
PRJ-2025-004663 | Al Noor Hospital | Greater Cairo | Emergency | Equipment Procurement | Medium | In Progress | Omar Hassan | Cerner | 2023-03-17 | 2023-04-13 | March | 27 | 6 | 24 | 25% | 945882.92 | 9026.37 | 2 | 20.8 | 5.2 | 459 | 5 | -0.46 | 0.29 | 10.06
PRJ-2025-004756 | Riverbend Hospital | Nile Delta | Surgery | Telehealth Rollout | Medium | Not Started | Nadia Mostafa | Cerner | 2023-03-05 | 2023-03-26 | March | 21 | 0 | 25 | 0% | 535834.43 | 148250.92 | 3 | 12.1 | 53.3 | 833.1 | 17 | 3.57 | -0.318 | -0.21
PRJ-2025-004757 | Central Medical Center | Greater Cairo | Emergency | Quality Improvement | Medium | Not Started | Hany Saleh | Epic | 2023-03-26 | 2023-04-23 | March | 28 | 0 | 110 | 0% | 146085.56 | 47946.62 | 0 | 13.4 | 12.6 | 381.2 | 4 | 1.67 | -0.216 | 1.31
PRJ-2025-004823 | Al Noor Hospital | Upper Egypt | Outpatient | Telehealth Rollout | Medium | In Progress | Mona Younis | Allscripts | 2023-03-27 | 2023-05-05 | March | 39 | 32 | 116 | 27.59% | 102117.87 | 16467.26 | 0 | 25.9 | 33.1 | 358.5 | 3 | -0.58 | 0.134 | 1.68
PRJ-2025-004849 | Green Valley Clinic | Alexandria | Emergency | New Wing Construction | Low | In Progress | Laila Ismail | Epic | 2023-03-22 | 2023-03-31 | March | 9 | 8 | 17 | 47.06% | 59172.48 | 10626.88 | 0 | 4.6 | 16.8 | 403.8 | 3 | 0.02 | 0.162 | -4.08
PRJ-2025-004853 | Green Valley Clinic | Upper Egypt | Emergency | Equipment Procurement | Critical | In Progress | Sarah Ibrahim | Epic | 2023-03-16 | 2023-03-25 | March | 9 | 9 | 20 | 45% | 551851.73 | 11257.3 | 2 | 38 | 80.1 | 93.6 | 3 | -0.29 | 0.199 | -0.49
PRJ-2025-004883 | Riverbend Hospital | Greater Cairo | Radiology | Regulatory Compliance | Critical | In Progress | Karim Ismail | Allscripts | 2023-03-10 | 2023-03-17 | March | 7 | 6 | 14 | 42.86% | 180413.48 | 159583.54 | 1 | 8.5 | 38.3 | 817.1 | 4 | -1.23 | -0.304 | -7.36
PRJ-2025-004899 | Central Medical Center | Greater Cairo | Pharmacy | Quality Improvement | High | In Progress | Farah Mahmoud | Cerner | 2023-03-17 | 2023-03-25 | March | 8 | 5 | 19 | 26.32% | 637052.54 | 464582.4 | 0 | 7.7 | 12.6 | 1224.9 | 6 | 0.67 | -0.037 | 2.46
PRJ-2025-004907 | Eastside Cardio Institute | Red Sea | Surgery | Regulatory Compliance | Critical | Completed | Tarek Ibrahim | Cerner | 2023-03-18 | 2023-03-30 | March | 12 | 29 | 29 | 100% | 312505.85 | 277112.35 | 0 | 47.5 | 27.1 | 2590.8 | 4 | 0.2 | 0.234 | 6.79
PRJ-2025-004925 | Central Medical Center | Greater Cairo | Emergency | Equipment Procurement | Critical | In Progress | Sarah El Sayed | Epic | 2023-03-15 | 2023-03-22 | March | 7 | 4 | 13 | 30.77% | 301335.95 | 5380.15 | 0 | 33.8 | 20.7 | 628.2 | 8 | -1.21 | 0.237 | 2.82
PRJ-2025-004956 | Green Valley Clinic | Nile Delta | OB/GYN | Equipment Procurement | High | In Progress | Farah El Sayed | Cerner | 2023-03-09 | 2023-04-08 | March | 30 | 47 | 125 | 37.6% | 82126.17 | 42307.06 | 3 | 7.5 | 9.3 | 4733.9 | 8 | -1.38 | 0.041 | 4.28
PRJ-2025-005006 | Central Medical Center | Greater Cairo | Radiology | Equipment Procurement | High | In Progress | Laila Ismail | Allscripts | 2023-03-30 | 2023-05-01 | March | 32 | 1 | 18 | 5.556% | 76358.75 | 48710.2 | 0 | 7.7 | 0.7 | 251.9 | 15 | -0.25 | 0.038 | -3.35
PRJ-2025-005018 | Central Medical Center | Alexandria | ID | EHR Upgrade | Medium | In Progress | Hassan El Sayed | Epic | 2023-03-19 | 2023-04-01 | March | 13 | 9 | 19 | 47.37% | 236461.26 | 220706.86 | 0 | 37.8 | 9.9 | 229.4 | 6 | -0.92 | -0.263 | -5.19
PRJ-2025-005052 | Riverbend Hospital | Upper Egypt | Pediatrics | Cybersecurity Hardening | Medium | In Progress | Hassan Ismail | Meditech | 2023-03-23 | 2023-05-02 | March | 40 | 1 | 53 | 1.887% | 139510.61 | 103586.04 | 0 | 10.5 | 53.7 | 1230.2 | 4 | -1.17 | 0.09 | 2.77
PRJ-2025-005122 | Sunrise Children’s | Greater Cairo | Outpatient | Telehealth Rollout | Critical | In Progress | Ahmed Farouk | Meditech | 2023-03-04 | 2023-04-01 | March | 28 | 5 | 11 | 45.45% | 42508.5 | 8620.05 | 0 | 27.7 | 9.8 | 2141.2 | 14 | 0.72 | 0.099 | 10.12
PRJ-2025-005252 | Eastside Cardio Institute | Upper Egypt | Surgery | EHR Upgrade | Medium | In Progress | Youssef Hassan | OpenMRS | 2023-03-19 | 2023-04-01 | March | 13 | 5 | 31 | 16.13% | 44535.03 | 1500.08 | 0 | 5.8 | 23.2 | 363.7 | 6 | 0.01 | -0.299 | 3.78
PRJ-2025-005502 | Central Medical Center | Greater Cairo | IM | EHR Upgrade | Low | In Progress | Farah El Sayed | OpenMRS | 2023-03-23 | 2023-03-30 | March | 7 | 4 | 18 | 22.22% | 217444.23 | 170005.22 | 0 | 22.1 | 33.3 | 1078.1 | 4 | -3.77 | -0.186 | 11.06
PRJ-2025-005609 | Al Noor Hospital | Nile Delta | Orthopedics | Telehealth Rollout | Medium | Not Started | Sarah Farouk | Epic | 2023-03-26 | 2023-04-15 | March | 20 | 0 | 21 | 0% | 263435.47 | 158716.3 | 0 | 24.4 | 8.7 | 957.5 | 3 | 0.92 | -0.074 | -1.71
PRJ-2025-005655 | Central Medical Center | Greater Cairo | Radiology | Equipment Procurement | Medium | In Progress | Ahmed Younis | Cerner | 2023-03-14 | 2023-03-30 | March | 16 | 14 | 77 | 18.18% | 80279.64 | 40119.55 | 0 | 5.2 | 42.8 | 951 | 3 | 0.6 | 0.025 | 6.98
PRJ-2025-005693 | St. Mary’s Health | Greater Cairo | Orthopedics | Telehealth Rollout | High | Completed | Tarek Ismail | Epic | 2023-03-18 | 2023-04-11 | March | 24 | 16 | 16 | 100% | 32111.35 | 19198.64 | 0 | 54.2 | 64.7 | 1420.6 | 6 | -0.96 | 0.046 | 7.54
PRJ-2025-005884 | Eastside Cardio Institute | Greater Cairo | IM | Equipment Procurement | Medium | In Progress | Karim Farouk | OpenMRS | 2023-03-27 | 2023-06-15 | March | 80 | 20 | 25 | 80% | 416517.43 | 258720.98 | 0 | 5.6 | 28.8 | 840.6 | 12 | -0.82 | -0.277 | 11.4
PRJ-2025-005888 | Sunrise Children’s | Alexandria | Emergency | Quality Improvement | High | In Progress | Karim Ismail | Allscripts | 2023-03-09 | 2023-03-24 | March | 15 | 3 | 16 | 18.75% | 286667.9 | 90564.23 | 1 | 15.3 | 9.2 | 415.4 | 4 | -0.98 | -0.153 | 2.69
PRJ-2025-005950 | Riverbend Hospital | Greater Cairo | Surgery | EHR Upgrade | Critical | In Progress | Mona Ibrahim | Epic | 2023-03-06 | 2023-03-18 | March | 12 | 6 | 21 | 28.57% | 26487.97 | 32271.76 | 8 | 21 | 22.8 | 512.4 | 3 | 0.57 | 0.29 | -0.87
PRJ-2025-005954 | St. Mary’s Health | Greater Cairo | Cardiology | Quality Improvement | High | In Progress | Mona Ibrahim | Epic | 2023-03-28 | 2023-04-22 | March | 25 | 184 | 500 | 36.8% | 132967.88 | 54971.6 | 1 | 31.3 | 34.1 | 742.4 | 4 | -1.5 | -0.202 | 4.94
PRJ-2025-006082 | Eastside Cardio Institute | Upper Egypt | Pediatrics | Quality Improvement | High | In Progress | Nadia Aziz | Cerner | 2023-03-23 | 2023-04-05 | March | 13 | 7 | 37 | 18.92% | 101418.7 | 22613.18 | 0 | 29.8 | 37.7 | 349.4 | 3 | 1.06 | -0.493 | 3.33
PRJ-2025-006093 | Central Medical Center | Alexandria | Emergency | EHR Upgrade | Critical | In Progress | Laila Hassan | Epic | 2023-03-17 | 2023-04-09 | March | 23 | 22 | 85 | 25.88% | 77898.8 | 52863.4 | 0 | 6.2 | 6.1 | 1033.8 | 5 | 0.73 | -0.368 | 7.34
PRJ-2025-006109 | Central Medical Center | Alexandria | Emergency | EHR Upgrade | High | In Progress | Dina Mahmoud | Cerner | 2023-03-10 | 2023-03-21 | March | 11 | 65 | 164 | 39.63% | 41432.17 | 18131.59 | 0 | 32.9 | 20.3 | 716 | 5 | 1.19 | -0.295 | -3.97
PRJ-2025-006134 | Central Medical Center | Greater Cairo | Cardiology | Regulatory Compliance | High | Completed | Nadia Ibrahim | Epic | 2023-03-28 | 2023-05-25 | March | 58 | 15 | 15 | 100% | 176808.4 | 58989.32 | 0 | 46.6 | 10.4 | 498.2 | 6 | -1.11 | -0.376 | 1.88
PRJ-2025-006228 | Eastside Cardio Institute | Greater Cairo | Emergency | Regulatory Compliance | High | In Progress | Hany Farouk | Cerner | 2023-03-13 | 2023-03-25 | March | 12 | 13 | 31 | 41.94% | 250085.68 | 191727.69 | 0 | 7.1 | 28.6 | 1048.2 | 4 | 0.87 | 0.135 | -0.06
PRJ-2025-006262 | Riverbend Hospital | Upper Egypt | Surgery | Quality Improvement | High | In Progress | Sarah Younis | Epic | 2023-03-19 | 2023-04-05 | March | 17 | 28 | 37 | 75.68% | 461236.27 | 48717.63 | 2 | 11.9 | 13.9 | 355.1 | 4 | -0.67 | -0.048 | 3.06
PRJ-2025-006362 | Al Noor Hospital | Sinai | Surgery | Equipment Procurement | Low | In Progress | Hany Mahmoud | Allscripts | 2023-03-13 | 2023-05-18 | March | 66 | 4 | 10 | 40% | 78219.81 | 34130.32 | 0 | 23.3 | 27.1 | 1115.7 | 5 | -2.43 | 0.001 | 6.29
PRJ-2025-006374 | Sunrise Children’s | Nile Delta | Emergency | Regulatory Compliance | Critical | In Progress | Hany Khaled | Epic | 2023-03-14 | 2023-04-03 | March | 20 | 28 | 68 | 41.18% | 34559.69 | 45703.19 | 0 | 80.5 | 26.7 | 163.6 | 5 | 0.16 | -0.009 | 8.31
PRJ-2025-006398 | Central Medical Center | Greater Cairo | Emergency | New Wing Construction | High | Completed | Hassan Aziz | Epic | 2023-03-17 | 2023-03-24 | March | 7 | 17 | 17 | 100% | 62534.45 | 22093.58 | 0 | 43 | 85.9 | 696.7 | 6 | 0.89 | -0.507 | -1.02
PRJ-2025-006524 | Central Medical Center | Greater Cairo | Emergency | Equipment Procurement | Medium | In Progress | Omar Ibrahim | Epic | 2023-03-20 | 2023-03-28 | March | 8 | 1 | 21 | 4.762% | 152283.43 | 24658.57 | 7 | 7.4 | 13.9 | 191.3 | 5 | -0.45 | -0.398 | -5.34
PRJ-2025-006531 | St. Mary’s Health | Greater Cairo | Surgery | Telehealth Rollout | Medium | In Progress | Laila Hamdy | Meditech | 2023-03-22 | 2023-05-08 | March | 47 | 26 | 105 | 24.76% | 202236.53 | 30255.58 | 1 | 30.3 | 8.6 | 232.3 | 10 | -2.87 | -0.024 | 4.59
PRJ-2025-006594 | Riverbend Hospital | Greater Cairo | Oncology | New Wing Construction | Critical | Not Started | Farah Younis | Epic | 2023-03-15 | 2023-05-12 | March | 58 | 0 | 10 | 0% | 856794.04 | 80884.54 | 0 | 5 | 4.4 | 713.4 | 8 | -1.54 | 0.061 | -8.62
PRJ-2025-006623 | Al Noor Hospital | Alexandria | Orthopedics | Telehealth Rollout | Low | In Progress | Farah Aziz | Epic | 2023-03-29 | 2023-04-08 | March | 10 | 8 | 13 | 61.54% | 26220.66 | 35637.12 | 8 | 7.2 | 19.3 | 384.6 | 4 | -1.36 | -0.186 | -1.79
PRJ-2025-006670 | Central Medical Center | Red Sea | Surgery | EHR Upgrade | Medium | In Progress | Amira Mahmoud | Allscripts | 2023-03-04 | 2023-03-11 | March | 7 | 51 | 133 | 38.35% | 253530.96 | 259277.42 | 1 | 12 | 17.8 | 466.4 | 3 | 2.49 | 0.172 | 6.37
PRJ-2025-006696 | Green Valley Clinic | Alexandria | ID | EHR Upgrade | Medium | In Progress | Tarek Mostafa | Epic | 2023-03-17 | 2023-03-26 | March | 9 | 15 | 26 | 57.69% | 39424.73 | 22282.48 | 1 | 27.1 | 27.3 | 2602 | 3 | 0.62 | 0.237 | 7.34
PRJ-2025-006744 | Riverbend Hospital | Nile Delta | Oncology | New Wing Construction | High | In Progress | Tarek Khaled | Epic | 2023-03-08 | 2023-04-07 | March | 30 | 2 | 11 | 18.18% | 103584.14 | 61067.48 | 0 | 8.9 | 53.7 | 943.3 | 10 | 0.44 | -0.088 | 3.15
PRJ-2025-006861 | Central Medical Center | Upper Egypt | Cardiology | Equipment Procurement | High | In Progress | Amira Saleh | Meditech | 2023-03-04 | 2023-04-09 | March | 36 | 50 | 91 | 54.95% | 92917.42 | 86244.77 | 0 | 6.7 | 34.3 | 611 | 10 | 0.26 | 0.277 | -3.39
PRJ-2025-006953 | Al Noor Hospital | Greater Cairo | Oncology | Telehealth Rollout | Medium | In Progress | Sarah Mahmoud | Cerner | 2023-03-25 | 2023-04-10 | March | 16 | 43 | 133 | 32.33% | 91915.67 | 4102.87 | 0 | 8.4 | 11.6 | 226.3 | 3 | -0.44 | -0.08 | 11.75
PRJ-2025-007060 | Sunrise Children’s | Greater Cairo | Oncology | EHR Upgrade | Medium | Not Started | Nadia Farouk | OpenMRS | 2023-03-26 | 2023-05-30 | March | 65 | 0 | 14 | 0% | 147002.9 | 78380.34 | 0 | 27.4 | 0.4 | 493.8 | 5 | -1.68 | -0.178 | -3.32
PRJ-2025-007098 | Central Medical Center | Alexandria | Oncology | New Wing Construction | Medium | In Progress | Sarah Aziz | Allscripts | 2023-03-02 | 2023-06-11 | March | 101 | 2 | 13 | 15.38% | 156511.9 | 32808.7 | 0 | 31.3 | 11.2 | 342 | 3 | 0.24 | 0.198 | 14.19
PRJ-2025-007131 | Central Medical Center | Alexandria | Orthopedics | New Wing Construction | Medium | In Progress | Karim Ismail | Cerner | 2023-03-09 | 2023-04-06 | March | 28 | 14 | 25 | 56% | 467586.22 | 337903.73 | 0 | 32.6 | 33.7 | 595.4 | 5 | 0.14 | -0.172 | 2.2
PRJ-2025-007141 | Sunrise Children’s | Greater Cairo | IM | EHR Upgrade | High | In Progress | Mona Mostafa | Epic | 2023-03-24 | 2023-03-31 | March | 7 | 2 | 13 | 15.38% | 26303.83 | 10569.5 | 1 | 18.4 | 7.7 | 698.9 | 8 | -3.54 | -0.03 | 9.85
PRJ-2025-007146 | Green Valley Clinic | Greater Cairo | Surgery | Cybersecurity Hardening | Critical | In Progress | Youssef Khaled | Cerner | 2023-03-23 | 2023-05-16 | March | 54 | 5 | 16 | 31.25% | 462677.2 | 256475.91 | 2 | 25.2 | 38.8 | 106.6 | 4 | -0.68 | -0.06 | 2.69
PRJ-2025-007167 | Riverbend Hospital | Nile Delta | Emergency | Process Automation | Critical | In Progress | Farah Younis | Epic | 2023-03-24 | 2023-05-24 | March | 61 | 7 | 42 | 16.67% | 783744.43 | 281368.22 | 0 | 8 | 24.3 | 511 | 3 | -1.67 | -0.121 | 4.12